RACI MATRIX

Inventory Mismatch Dispute Resolution — E-Commerce Supply Chain

Prepared by: Karthika Ayyanan  |  Version: v1.0  |  Date: April 20, 2026  |  Status: Draft

# 1. Overview

This RACI Matrix defines the roles and responsibilities of all stakeholders involved in the Inventory Mismatch Dispute Resolution project. Each task is mapped to show who is Responsible, Accountable, Consulted, and Informed — ensuring clarity and accountability throughout the investigation and resolution process.

# 2. RACI Legend

| R — Responsible — Who DOES the work | A — Accountable — Who is ANSWERABLE for outcome | C — Consulted — Who provides INPUT before decisions | I — Informed — Who is KEPT IN THE LOOP |
| --- | --- | --- | --- |

# 3. RACI Matrix

| Task / Activity | SnapMart | QuickKart | Logistics Partner | BA |
| --- | --- | --- | --- | --- |
| Submit Dispatch Records | R/A | I | — | C |
| Submit Warehouse Receiving Logs | I | R/A | — | C |
| Submit POD (Proof of Delivery) | I | C | R/A | — |
| Raise Formal Dispute Ticket | R/A | I | — | C |
| Investigate Root Cause | C | C | I | R/A |
| Communicate Investigation Findings | I | R | I | A |
| Block Seller Listing | I | R/A | — | C |
| Conduct Resolution Meeting | C | R/A | I | C |
| Implement Preventive Measures | R | R/A | I | C |
| Document Resolution Outcome | I | I | I | R/A |

# 4. Key Notes

| Rule | Description |
| --- | --- |
| One Accountable | Every task has exactly one accountable party — clear ownership prevents disputes about responsibility |
| R/A Combined | Where one party both does the work and is accountable, R/A is combined in a single cell |
| BA Role | The BA is primarily Responsible/Accountable for investigation tasks but Consulted on operational tasks |
| Logistics Partner | The Logistics Partner is primarily Responsible for POD submission and Informed on resolution outcomes |
| SnapMart/QuickKart | Both are jointly Responsible for implementing preventive measures as the dispute involves both parties |

BA Portfolio Project  |  Karthika Ayyanan  |  v1.0  |  April 2026  |  Draft